## Instructions
The Excel PowerPivot Gant Chart
How to use this Spreadsheet
If you don't have PowerPivot
| 1 | Ensure that you have access to Office 2010
| 2 | Goto this link to download PowerPivot add-in
remember, download X86 version for 32 bit and amd64 for 64 bit
Don't worry - it's free…
Using this Spreadsheet
| 1 | Select the "Days" tab and set the following
Set the days that you want to include in column D. Ie If you want to include weekends, set Sat and Sun to 1
| 2 | Enter tasks in the "Tasks" tab
Leave the first record on row 3. This will calculate the start and end of the project and make sure that the report span is correct
Enter all other information as required. Make sure that start and end dates are provided for each task
| 3 | Go to PowerPivot window to ensure that the entries you've made are recorded in PowerPivot
| 4 | Return to Excel, "Gant" tab and click Data > Refresh All
And Then… why not upload your project to SharePoint and share with everyone involved so that they can monitor their tasks.

## Gant
CRM Implementation
Elapsed Time Gant
Gant | [5 empty] | Column Labels
[6 empty] | 7/27/2012 |  |  |  |  | 8/3/2012 |  |  |  |  | 8/10/2012 |  |  |  |  | 8/17/2012 |  |  |  |  | 8/24/2012 |  |  |  |  | 8/31/2012 |  |  |  |  | 9/7/2012 |  |  |  |  | 9/14/2012 |  |  |  |  | 9/21/2012 |  |  |  |  | 9/28/2012 |  |  |  |  | 10/5/2012 |  |  |  |  | 10/12/2012 |  |  |  |  | 10/19/2012 |  |  |  |  | 10/26/2012 |  |  |  |  | 11/2/2012 |  |  |  |  | 11/9/2012 |  |  |  |  | 11/16/2012 |  |  |  |  | 11/23/2012 |  |  |  |  | 11/30/2012
[6 empty] | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7 | 3 | 4 | 5 | 6 | 7
Row Labels | Description | Start | End | Responsible | Percent | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
CRM
Scoping
| Document scope findings | 8/17/2012 | 8/19/2012 | David | 75% | bar: 8/17/2012 7
| Initial discovery meetings - Finance | 8/3/2012 | 8/8/2012 | Rob | 90% | bar: 8/3/2012 7 to 8/10/2012 5
| Initial discovery meetings - Operations | 8/12/2012 | 8/16/2012 | Colin | 100% | 8/17/2012 3: 2; 8/17/2012 4: 2; 8/17/2012 5: 2; 8/17/2012 6: 2
| Initial discovery meetings - Sales | 7/24/2012 | 7/31/2012 | David | 100% | 7/27/2012 4: 2; 7/27/2012 5: 2; 7/27/2012 6: 2; 7/27/2012 7: 2; 8/3/2012 3: 2; 8/3/2012 4: 2
Design
| Define data collection requirements | 8/20/2012 | 8/30/2012 | Rob | 50% | bar: 8/24/2012 3 to 8/31/2012 6
| Define reporting requirements | 8/20/2012 | 8/30/2012 | Rob | 10% | bar: 8/24/2012 3 to 8/31/2012 6
| Define workflow and approval requirements | 8/20/2012 | 8/30/2012 | Colin | 20% | bar: 8/24/2012 3 to 8/31/2012 6
Development
| Develop account forms | 9/1/2012 | 9/15/2012 | David | 0% | bar: 9/7/2012 3 to 9/14/2012 7
| Develop opportunity forms | 9/1/2012 | 9/15/2012 | Colin | 0% | bar: 9/7/2012 3 to 9/14/2012 7
| Develop quote forms | 9/1/2012 | 9/15/2012 | David | 0% | bar: 9/7/2012 3 to 9/14/2012 7
| Develop task forms | 9/16/2012 | 9/25/2012 | Rob | 0% | bar: 9/21/2012 3 to 9/28/2012 4
| Develop workflow | 9/16/2012 | 9/25/2012 | David | 0% | bar: 9/21/2012 3 to 9/28/2012 4
FAT
| Collate feedback from FAT | 10/17/2012 | 10/20/2012 | David | 0% | bar: 10/19/2012 5 to 10/19/2012 7
| FAT Signoff | 10/16/2012 | 10/16/2012 | Super Users | 0% | bar: 10/19/2012 4
| Functional Acceptance testing by super users | 10/1/2012 | 10/15/2012 | Super Users | 0% | bar: 10/5/2012 3 to 10/19/2012 3
| Rework Development | 10/21/2012 | 10/31/2012 | Rob | 0% | bar: 10/26/2012 3 to 11/2/2012 5
Go Live
| Go / No-go Decision | 11/30/2012 | 11/30/2012 | All | 0% | bar: 11/30/2012 7
Train & Document
| Documentation | 9/16/2012 | 9/30/2012 | Rob | 0% | bar: 9/21/2012 3 to 9/28/2012 7
| Super User Training | 9/26/2012 | 9/30/2012 | Colin | 0% | bar: 9/28/2012 5 to 9/28/2012 7
UAT
| User Acceptance testing by super users | 11/1/2012 | 11/15/2012 | Super Users | 0% | bar: 11/2/2012 6 to 11/16/2012 6
LC
| Full Project Life Cycle | 7/21/2012 | 11/30/2012 | All | 0% | bar: 7/27/2012 3 to 11/30/2012 7
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Tasks
Start | End | Description | Category1 | Category2 | Responsible | Pct_Complete
2012-07-21 | 2012-11-30 | Full Project Life Cycle | LC |  | All
2012-07-24 | 2012-07-31 | Initial discovery meetings - Sales | CRM | Scoping | David | 100%
2012-08-03 | 2012-08-08 | Initial discovery meetings - Finance | CRM | Scoping | Rob | 90%
2012-08-12 | 2012-08-16 | Initial discovery meetings - Operations | CRM | Scoping | Colin | 100%
2012-08-17 | 2012-08-19 | Document scope findings | CRM | Scoping | David | 75%
2012-08-20 | 2012-08-30 | Define data collection requirements | CRM | Design | Rob | 50%
2012-08-20 | 2012-08-30 | Define workflow and approval requirements | CRM | Design | Colin | 20%
2012-08-20 | 2012-08-30 | Define reporting requirements | CRM | Design | Rob | 10%
2012-09-01 | 2012-09-15 | Develop account forms | CRM | Development | David
2012-09-01 | 2012-09-15 | Develop opportunity forms | CRM | Development | Colin
2012-09-01 | 2012-09-15 | Develop quote forms | CRM | Development | David
2012-09-16 | 2012-09-25 | Develop task forms | CRM | Development | Rob
2012-09-16 | 2012-09-25 | Develop workflow | CRM | Development | David
2012-09-26 | 2012-09-30 | Super User Training | CRM | Train & Document | Colin
2012-09-16 | 2012-09-30 | Documentation | CRM | Train & Document | Rob
2012-10-01 | 2012-10-15 | Functional Acceptance testing by super users | CRM | FAT | Super Users
2012-10-16 | 2012-10-16 | FAT Signoff | CRM | FAT | Super Users
2012-10-17 | 2012-10-20 | Collate feedback from FAT | CRM | FAT | David
2012-10-21 | 2012-10-31 | Rework Development | CRM | FAT | Rob
2012-11-01 | 2012-11-15 | User Acceptance testing by super users | CRM | UAT | Super Users
2012-11-30 | 2012-11-30 | Go / No-go Decision | CRM | Go Live | All
2012-12-01 | 2012-01-01 | Completion | CRM | Go Live | All
Formulas:
Start = MIN([Start, row below]:B1048576)-WEEKDAY(MIN([Start, row below]:B1048576),16)+1
End = MAX([End, row below]:C1048576)-WEEKDAY(MAX([End, row below]:C1048576),16)+7

## Days
Day_Abb | Day_Show | Day_Add | Include | Day_Of_Week
Sun | S | 5 | 0 | 2
Mon | M | 4 | 1 | 3
Tue | T | 3 | 1 | 4
Wed | W | 2 | 1 | 5
Thu | T | 1 | 1 | 6
Fri | F | 0 | 1 | 7
Sat | S | 6 | 0 | 1